## Worksheet
Project | Start Date | End Date
Theme Park | 18-08-2025 | 18-08-2025
Stage | Activity Name | Category | Qc | Progress | Next Day Plan | Remarks | Status | created_at | created_by
PRELIMINARY WORKS | Site Cleaning & Shed Work | work | Testing & Inspection | 100 | Next day needs to work on foot marking | site cleaning and shed work in progress | completed | 18-08-2025 | Sridhar
PRELIMINARY WORKS | Footing Marking | work | Materials Quality | 100 | needs to extend this | extend due to some technical issues | completed | 18-08-2025 | Sridhar
SUB-STRUCTURE WORKS | Excavation For Footing and Sump | work | Materials Quality | 69 | next day wrk | rmrk | save | 18-08-2025 | Sridhar
SUPER STRUCTURE WORKS | GF Column Concrete | work | Materials Quality | 56 | nxt dyk | rmrkk | save | 18-08-2025 | Sridhar
SUPER STRUCTURE WORKS | PCC For Flooring | block | Testing & Inspection |  | New Additions | new | save | 18-08-2025 | Sridhar