## Sheet1
SL.NO | ACTIVITY | DURATION (DAYS) | START DATE | END DATE
Stages | PRELIMINARY WORKS | 1 | 2025-07-02 | 2025-07-03
Activities | Site Cleaning & Shed Work
Activities | Footing Marking
Stages | SUB-STRUCTURE WORKS | 3 | 2025-07-04 | 2025-07-06
Activities | Excavation For Footing and Sump
Activities | Trimming Work For Footings
Activities | PCC For Footing
Activities | Column Position Marking
Activities | Consolidation Work/ Column Starter Concrete
Stages | SUPER STRUCTURE WORKS | 3 | 2025-07-07 | 2025-07-09
Activities | GF Column Concrete
Activities | PCC For Flooring
Stages | FINISHING WORKS | 5 | 2025-07-10 | 2025-07-14
Activities | GF Flooring Work & Toilet tiling
Activities | FF Flooring Work & Toilet tiling