## Sheet1
SL.NO | ACTIVITY | DURATION (DAYS) | START DATE | END DATE
Stages | PRELIMINARY WORKS
Activities | Site Cleaning & Shed Work | 1 | 2025-07-02 | 2025-07-02
Activities | Footing Marking | 1 | 2025-07-02 | 2025-07-02
Stages | SUB-STRUCTURE WORKS
Activities | Excavation For Footing and Sump | 1 | 2025-07-02 | 2025-07-02
Activities | Trimming Work For Footings | 1 | 2025-07-02 | 2025-07-02
Activities | PCC For Footing | 1 | 2025-07-02 | 2025-07-02
Activities | Column Position Marking | 1 | 2025-07-02 | 2025-07-02
Activities | Consolidation Work/ Column Starter Concrete | 2 | 2025-07-03 | 2025-07-04
Stages | SUPER STRUCTURE WORKS
Activities | GF Column Concrete | 2 | 2025-07-05 | 2025-07-06
Activities | PCC For Flooring | 1 | 2025-07-07 | 2025-07-07
Stages | FINISHING WORKS
Activities | GF Flooring Work & Toilet tiling | 5 | 2025-07-08 | 2025-07-12
Activities | FF Flooring Work & Toilet tiling | 5 | 2025-07-13 | 2025-07-17